## Master Task Board
🚀 STROM — AGENTIC TRADING PLATFORM · ANTIGRAVITY MISSION CONTROL · v2.0
LEGEND ▸ 🟢 Parallel Group = tasks that can run simultaneously across agents ▸ 🔴 Depends On = must complete BEFORE this task starts ▸ ⚡ Critical Path = blocks many downstream tasks ▸ Agents: BackendAgent ¦ FrontendAgent ¦ QAAgent ¦ DevOpsAgent ¦ DocsAgent ¦ AgentsAgent ▸ Brokers: Dhan + Paper ▸ Crypto: Binance/Bybit adapter ▸ Context files: paste into Antigravity task context
Task ID | Title | Workstream | Antigravity Agent | Depends On | Parallel Group | Can Run Parallel With | Description | Files / Modules | Acceptance Criteria | Completion Verification | Complexity | Status | Context Files to Attach | Priority
═══ BACKEND WORKSTREAM · Paste into → BackendAgent ═══
B1 | Project Scaffold & Config | Backend | BackendAgent | None (kickoff) | PG-1 (Kickoff) | F1, D1, Q1, P5 | Initialize FastAPI project: pyproject.toml, pydantic-settings config, /health endpoint, CORS (localhost:3000), structured JSON logging (structlog), global error handler returning {error, detail, correlation_id}. Create directory structure per WORKFLOW.md. | packages/api/pyproject.toml src/main.py src/config.py src/__init__.py | ✅ GET /health → 200 {status: ok, version: x} ✅ Config loads from .env via pydantic-settings ✅ CORS allows localhost:3000 ✅ Structured JSON logs to stdout ✅ Error handler: 4xx/5xx return {error, detail, correlation_id} ✅ pytest test_health.py passes | RUN: uvicorn src.main:app → starts RUN: curl localhost:8000/health → 200 RUN: pytest tests/ → pass CHECK: .env.example has all keys | S | Not Started | RULES.md, WORKFLOW.md, SPECS.md | ⚡Critical
B2 | Database Models & Migrations | Backend | BackendAgent | B1 | PG-2 (Foundation) | B3, B13, F8 | SQLAlchemy 2.0 async models for ALL tables from SPECS.md: trade_log, strategy_registry, strategy_performance, audit_log, orders, positions. Alembic setup with async driver (asyncpg). Audit_log is INSERT-ONLY (no update/delete at app layer). All indexes from SPECS.md. | src/models/db.py src/models/trade.py src/models/order.py src/models/portfolio.py src/models/audit.py migrations/env.py migrations/versions/001_initial.py | ✅ alembic upgrade head → creates all 6 tables ✅ alembic downgrade -1 → clean rollback ✅ All columns match SPECS.md schemas exactly ✅ All indexes created ✅ audit_log: app-layer block on UPDATE/DELETE ✅ Async session factory works | RUN: alembic upgrade head → success RUN: alembic downgrade -1 → success RUN: psql \dt → 6 tables RUN: pytest tests/test_models.py → pass | M | Not Started | RULES.md, SPECS.md | ⚡Critical
B3 | Event Bus — Redis Streams | Backend | BackendAgent | B1 | PG-2 (Foundation) | B2, B13, F8 | Redis Streams wrapper implementing EventBus interface from SPECS.md: publish(), subscribe() with consumer groups, create_group(), ack(), health_check(). All 10 stream names as constants (market.ticks, signals.features, signals.generated, risk.decisions, orders.submitted, orders.filled, portfolio.updated, agents.lifecycle, alerts.triggered, system.killswitch). Backpressure: pause publisher if consumer lag > 100 msgs. | src/events/bus.py src/events/publishers.py src/events/consumers.py src/events/streams.py (constants) | ✅ publish() → message appears in stream ✅ subscribe() with consumer group → messages consumed ✅ Consumer group rebalance works ✅ Backpressure: lag > 100 → pause + alert ✅ health_check() → True when Redis up ✅ All 10 stream names defined ✅ ack() confirms processing | RUN: pytest tests/test_event_bus.py → pass RUN: publish 1000 msgs → all consumed TEST: backpressure triggers at threshold | M | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
B4 | Market Data Service + Mock Vendor | Backend | BackendAgent | B1, B3 | PG-3 (Services) | B5, B8, B11, F3 | Abstract DataVendorAdapter interface from SPECS.md. Implement MockDataVendor with sample NIFTY/BANKNIFTY option chain data (from fixtures). MarketDataService normalizes to OptionChainResponse, publishes to market.ticks. Stale detection: timestamp > 30s old → stale=true. API: GET /api/v1/market-data/option-chain/{underlying}?expiry=YYYY-MM-DD. Also GET /api/v1/market-data/features/{underlying} for computed features. | src/services/market_data_service.py src/adapters/data_vendor/base.py src/adapters/data_vendor/mock.py src/routers/market_data.py | ✅ Mock returns valid OptionChainResponse ✅ GET /market-data/option-chain/NIFTY → 200 ✅ GET /market-data/option-chain/BANKNIFTY → 200 ✅ Publishes to market.ticks stream ✅ Stale data flagged correctly (>30s) ✅ 404 for invalid underlying ✅ Data vendor health_check works | RUN: pytest tests/test_market_data.py → pass RUN: curl /api/v1/market-data/option-chain/NIFTY → valid JSON CHECK: Redis stream has message after call | M | Not Started | RULES.md, SPECS.md, SKILLS.md | High
B4a | Dhan Broker Adapter | Backend | BackendAgent | B2, B3, B8 | PG-3 (Services) | B4b | Implement DhanBrokerAdapter extending BrokerAdapter ABC from SPECS.md. Dhan API integration: (1) OAuth token flow via DhanHQ API, (2) place_order → Dhan order API, (3) get_order_status → poll/websocket, (4) cancel_order, (5) get_positions, (6) get_margins. Map Dhan instrument tokens to internal instrument format. Handle Dhan-specific: order types (MIS/CNC/CO/BO), product types, exchange segments (NSE_FNO). Rate limiting per Dhan docs (10 req/sec). Error mapping: Dhan error codes → internal error types. Config: DHAN_CLIENT_ID, DHAN_ACCESS_TOKEN in env. | src/adapters/broker/dhan.py src/adapters/broker/dhan_mappings.py tests/test_dhan_adapter.py | ✅ Implements all 5 BrokerAdapter methods ✅ OAuth token handling (access token refresh) ✅ Order placement with correct Dhan payload ✅ Instrument token mapping (NIFTY weekly, BANKNIFTY weekly) ✅ Rate limiting: 10 req/sec enforced ✅ Error codes mapped to internal types ✅ Credentials from env only (never logged) ✅ Mock mode for testing without live Dhan API ✅ Supports MIS and NRML product types | RUN: pytest tests/test_dhan_adapter.py → pass (mock mode) CHECK: No DHAN_ACCESS_TOKEN in any log output TEST: rate limiter rejects > 10 req/sec TEST: instrument mapping NIFTY → correct token | M | Not Started | RULES.md, SPECS.md | High
B4b | Crypto Data Vendor + Broker Adapter | Backend | BackendAgent | B2, B3, B8 | PG-3 (Services) | B4a | Implement CryptoBrokerAdapter (Binance/Bybit) extending BrokerAdapter ABC. Implement CryptoDataVendor extending DataVendorAdapter. KEY DIFFERENCES from equity: (1) 24/7 market — time_of_day risk rule = 'always_open', (2) fractional qty (BTC 0.001 lots), (3) cross/isolated margin modes, (4) different fee structure (maker/taker), (5) WebSocket for real-time prices (not polling). Normalize crypto data to same FeatureVector schema where possible; add crypto-specific fields (funding_rate, open_interest_usd, liquidation_levels). Config: CRYPTO_EXCHANGE=binance¦bybit, CRYPTO_API_KEY, CRYPTO_API_SECRET. | src/adapters/broker/crypto.py src/adapters/broker/crypto_mappings.py src/adapters/data_vendor/crypto.py src/adapters/data_vendor/crypto_ws.py tests/test_crypto_adapter.py | ✅ CryptoBrokerAdapter: all 5 methods implemented ✅ CryptoDataVendor: get_option_chain → crypto-equivalent orderbook/chain ✅ Fractional qty supported (0.001 BTC) ✅ 24/7 mode: no time-of-day rejection ✅ WebSocket real-time price feed ✅ Funding rate, OI in USD in features ✅ Margin mode (cross/isolated) configurable ✅ Fee calculation (maker/taker rates) ✅ Supports both Binance and Bybit via config ✅ Mock mode for testing ✅ Credentials from env only | RUN: pytest tests/test_crypto_adapter.py → pass (mock mode) TEST: fractional qty 0.001 → accepted TEST: time_of_day rule disabled for crypto CHECK: no API keys in logs | L | Not Started | RULES.md, SPECS.md | High
B5 | Feature Computation Engine | Backend | BackendAgent | B4 | PG-3 (Services) | B6, B8 | ALL deterministic computations: Black-Scholes Greeks (delta, gamma, theta, vega), IV surface, PCR, OI change (top 5 CE/PE), RSI-14, ATR-14, VWAP deviation, max pain. Output: FeatureVector from SPECS.md. Crypto extension: add funding_rate, liquidation_density, orderbook_imbalance to FeatureVector when asset_class=crypto. Test fixtures with known reference values. | src/utils/greeks.py src/utils/indicators.py src/utils/crypto_indicators.py src/services/signal_engine.py (feature part) | ✅ Greeks match Black-Scholes reference (tolerance 0.01) ✅ PCR, max pain, OI changes correct vs fixtures ✅ RSI, ATR, VWAP match TA-Lib reference ✅ Edge: zero volume, missing strikes, single strike → handled ✅ Returns null (not crash) on insufficient data ✅ Crypto indicators: funding_rate, orderbook_imbalance computed ✅ Fixtures in data/fixtures/ with reference values | RUN: pytest tests/test_greeks.py → pass RUN: pytest tests/test_indicators.py → pass RUN: pytest tests/test_crypto_indicators.py → pass CHECK: data/fixtures/ has reference files | L | Not Started | RULES.md, SPECS.md, SKILLS.md | High
B6 | Signal Engine + Strategy Framework | Backend | BackendAgent | B5, B2 | PG-4 (Core Logic) | B7 | Strategy execution framework with 3 sample strategies: (1) Iron Condor — sell OTM CE+PE in ranging regime, (2) Directional Momentum — buy ATM on breakout, (3) SMC Reversal — order block + FVG confluence entry. Strategy registry CRUD: POST/GET/PUT /api/v1/strategies. evaluate_signal() → TradeSignal. Each strategy declares regime_affinity and asset_class (equity¦crypto¦both). SMC indicators: order blocks, FVGs, BOS/CHoCH, liquidity sweeps added to indicators.py. | src/services/signal_engine.py src/services/strategy_registry.py src/utils/smc_indicators.py src/routers/strategies.py | ✅ Strategy CRUD works via API ✅ Iron Condor: correct signals for ranging fixture ✅ Momentum: correct signals for trending fixture ✅ SMC Reversal: correct signals for order-block fixture ✅ NO_SIGNAL when regime doesn't match affinity ✅ Signal schema = TradeSignal from SPECS.md ✅ Strategy registry persists to DB ✅ asset_class field filters strategies correctly ✅ SMC indicators: order_block, fvg, bos, choch computed | RUN: pytest tests/test_signal_engine.py → pass (4+ cases per strategy) RUN: pytest tests/test_smc_indicators.py → pass RUN: pytest tests/test_strategy_crud.py → pass TEST: POST → GET → evaluate_signal works | L | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
B7 | Risk Engine (Deterministic) | Backend | BackendAgent | B2, B6 | PG-4 (Core Logic) | B9 | ALL 8 risk rules as pure Python — NO LLM. From RULES.md: max_position_size, max_portfolio_delta, max_daily_loss, max_drawdown, margin_check, time_of_day, correlation_limit, single_concentration. ADDITIONS for multi-asset: (9) asset_class_exposure_limit (max % in crypto), (10) crypto-specific: max_leverage_check. Default on ANY error = REJECT. Risk approval includes timestamp (TTL 60s). check_risk() → RiskDecision. Crypto mode: time_of_day='always_open'. | src/services/risk_engine.py src/routers/risk.py | ✅ Each of 10 rules has ≥2 tests (pass + fail) ✅ REJECT on error (simulate crash → REJECT) ✅ Risk approval includes timestamp ✅ POST /risk/check → RiskDecision ✅ GET /risk/state → utilization % ✅ NO override path exists (test: force APPROVE impossible) ✅ Boundary: exact-at-limit values correct ✅ Crypto: time_of_day='always_open' when asset=crypto ✅ Crypto: leverage check enforced ✅ asset_class_exposure: max 30% in crypto (configurable) | RUN: pytest tests/test_risk_engine.py → all pass (min 24 cases) RUN: test_risk_no_bypass → proves no override CHECK: coverage 100% on risk_engine.py | L | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
B8 | Paper Trading Adapter | Backend | BackendAgent | B2, B3 | PG-3 (Services) | B4, B5, B4a, B4b | BrokerAdapter ABC from SPECS.md + PaperTradingAdapter. Simulates: order submission (instant), fill (0.5–2s delay), slippage (configurable 0–0.5%), cancellation, rate limiting (10/sec). Full lifecycle: PENDING→OPEN→FILLED/CANCELLED. Supports both equity lots and crypto fractional qty. Virtual capital tracking (default ₹10L equity + $10K crypto). | src/adapters/broker/base.py src/adapters/broker/paper.py | ✅ All 5 BrokerAdapter methods implemented ✅ Order lifecycle transitions correct ✅ Configurable slippage applied ✅ Rate limiting: >10/sec → RATE_LIMITED ✅ Cancel works for PENDING/OPEN only ✅ FILLED cannot be cancelled (test) ✅ Fractional crypto qty supported ✅ Virtual capital tracked correctly | RUN: pytest tests/test_paper_broker.py → pass TEST: lifecycle PENDING→OPEN→FILLED TEST: crypto 0.001 BTC order fills correctly | M | Not Started | RULES.md, SPECS.md | High
B9 | Execution Gateway | Backend | BackendAgent | B7, B8 | PG-5 (Integration) | B10 | Order placement service: MUST have valid risk approval < 60s old. Flow: signal → risk check → broker adapter → fill tracking → event publishing. Broker selection: reads BROKER_ADAPTER env (paper¦dhan¦crypto) and routes to correct adapter. API: POST /orders, GET /orders/{id}, DELETE /orders/{id}. Publishes to orders.submitted and orders.filled. All orders logged to audit_log. | src/services/execution_gateway.py src/routers/orders.py | ✅ Cannot place order without risk approval (403) ✅ Cannot place with stale approval >60s (403) ✅ Publishes to orders.submitted ✅ Fill tracking publishes to orders.filled ✅ Cancel works for pending ✅ All events logged to audit_log ✅ Correct broker adapter selected by config ✅ API schemas match SPECS.md | RUN: pytest tests/test_execution.py → pass TEST: no_risk_bypass → 403 TEST: stale_approval → 403 TEST: broker routing: paper vs dhan vs crypto | M | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
B10 | Portfolio Manager | Backend | BackendAgent | B4, B8, B2 | PG-5 (Integration) | B9, B11 | Position tracking: update on fill, compute realized+unrealized P&L, aggregate Greeks, track margin. Multi-asset: separate equity and crypto portfolios with combined view. API: GET /portfolio (query: asset_class=all¦equity¦crypto). Subscribes to orders.filled → auto-update. Publishes to portfolio.updated. | src/services/portfolio_manager.py src/routers/portfolio.py | ✅ Positions update on fill event ✅ P&L correct (test with known prices) ✅ Greeks aggregate correctly ✅ Margin utilization tracked ✅ Subscribes to orders.filled ✅ Publishes to portfolio.updated ✅ Equity + crypto separate + combined view ✅ API returns PortfolioState schema | RUN: pytest tests/test_portfolio.py → pass TEST: fill → position update → P&L calc TEST: combined portfolio (equity + crypto) | M | Not Started | RULES.md, SPECS.md | High
B11 | WebSocket Gateway | Backend | BackendAgent | B3, B1 | PG-3 (Services) | B4, B5, B8, B10 | FastAPI WebSocket at /api/v1/ws. Bridges Redis Streams → frontend. Channel subscription (subscribe/unsubscribe JSON). JWT auth on connect. Server heartbeat 15s. 3 missed pongs → disconnect. Protocol per SPECS.md. Supports multiple concurrent clients. | src/routers/ws.py | ✅ Connects with valid JWT ✅ Rejects without token (401) ✅ Subscribe/unsubscribe works ✅ Events arrive <100ms of Redis publish ✅ Heartbeat ping/pong works ✅ 3 missed pongs → disconnect ✅ Multiple concurrent clients supported | RUN: pytest tests/test_websocket.py → pass TEST: subscribe → trigger → receive <100ms TEST: auth required | M | Not Started | RULES.md, SPECS.md | High
B12 | Admin API + Kill Switch | Backend | BackendAgent | B3, B9 | PG-5 (Integration) | B10 | POST /admin/killswitch: cancel ALL pending orders (all brokers: paper+dhan+crypto), halt agents, optionally flatten, publish system.killswitch, send CRITICAL alert. POST /admin/reset: re-enable. GET /admin/agents: list active. GET/PATCH /admin/config. POST /admin/mode: switch advisory↔semi-auto. Kill switch completes in <2s. | src/routers/admin.py | ✅ Kill switch cancels all pending (all brokers) ✅ Publishes to system.killswitch ✅ No new orders post-killswitch (423 Locked) ✅ POST /admin/reset re-enables ✅ GET /admin/agents returns status list ✅ Completes in <2 seconds (timed test) ✅ CRITICAL alert sent ✅ Mode switch: advisory ↔ semi-auto | RUN: pytest tests/test_killswitch.py → pass TEST: post_killswitch_blocked → 423 TEST: reset re-enables TEST: timing <2s | M | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
B13 | Audit Logging Middleware | Backend | BackendAgent | B2, B1 | PG-2 (Foundation) | B3 | Middleware logging ALL POST/PUT/PATCH/DELETE to audit_log. Fields: timestamp, agent_id, action, inputs (sanitized), outputs, correlation_id. Credential patterns stripped. GET /admin/audit-logs with filters. INSERT-only enforcement. | src/models/audit.py src/middleware/audit.py | ✅ All state-changing requests auto-logged ✅ correlation_id in every log ✅ Credentials stripped from inputs ✅ GET /admin/audit-logs with filters ✅ INSERT-only (no UPDATE/DELETE test) ✅ No PII in logs | RUN: pytest tests/test_audit.py → pass TEST: API call → audit_log entry exists TEST: credential patterns not in logs | S | Not Started | RULES.md, SPECS.md | High
B14 | Backtest Runner | Backend | BackendAgent | B5, B6, B7 | PG-6 (Advanced) | B15 | Run strategy on historical data. Metrics: total return, Sharpe, max drawdown, win rate, equity curve. Respects risk rules in simulation. Supports equity and crypto historical data. API: POST /strategies/{id}/backtest. Results → strategy_performance table. Reject if <30 trading days. | src/services/backtest_runner.py src/routers/strategies.py (backtest) | ✅ Correct metrics for known fixture ✅ Missing data → skip day + warning ✅ Risk rules applied in simulation ✅ Results saved to strategy_performance ✅ Returns BacktestSummary schema ✅ Rejects <30 days data ✅ Works for equity + crypto strategies | RUN: pytest tests/test_backtest.py → pass TEST: POST /strategies/iron_condor_v2/backtest → metrics | L | Not Started | RULES.md, SPECS.md, SKILLS.md | Medium
B15 | Onboarding API | Backend | BackendAgent | B4, B8, B4a, B4b, B6, B7 | PG-6 (Advanced) | B16 | Onboarding flow APIs: POST /onboarding/broker-connect (validate broker creds, store in secrets mgr), POST /onboarding/risk-profile (save risk params), POST /onboarding/strategies (activate selected strategies), POST /onboarding/instruments (select underlyings + crypto pairs), GET /onboarding/status (completion state). Marks user as onboarded after all 4 steps complete. Returns available brokers: [paper, dhan] + crypto exchanges: [binance, bybit]. | src/routers/onboarding.py src/services/onboarding_service.py | ✅ Broker connect: validates connection, stores securely ✅ Risk profile: saves to config ✅ Strategy selection: activates chosen strategies ✅ Instrument selection: persists watchlist ✅ Status: tracks 4-step completion ✅ Available brokers list: paper, dhan ✅ Available crypto: binance, bybit ✅ Credentials never logged | RUN: pytest tests/test_onboarding.py → pass TEST: complete 4-step flow TEST: status reflects completion | M | Not Started | RULES.md, SPECS.md | High
B16 | Backend Integration Tests | Backend | BackendAgent | B4–B15 | PG-7 (Validation) | Q5 | E2E tests: (1) full equity trading cycle tick→signal→risk→order→fill→portfolio, (2) full crypto cycle, (3) risk rejection blocks order, (4) stale data → no signal, (5) kill switch stops everything (all brokers), (6) concurrent signals, (7) Dhan adapter mock integration, (8) onboarding flow. Paper broker + mock data. | tests/integration/ | ✅ Equity full cycle passes ✅ Crypto full cycle passes ✅ Risk rejection test passes ✅ Stale data → no signal ✅ Kill switch cancels all (paper+dhan+crypto) ✅ Concurrent 3 signals handled ✅ Dhan mock integration passes ✅ Onboarding flow passes ✅ All tests < 60 seconds total | RUN: pytest tests/integration/ -v → all pass CHECK: no shared state between tests | L | Not Started | RULES.md, WORKFLOW.md, SPECS.md | ⚡Critical
═══ AGENTIC RUNTIME · Paste into → BackendAgent (or dedicated AgentsAgent) ═══
A1 | Agent Base Class + Registry | Agents | BackendAgent | B1, B3 | PG-2 (Foundation) | B2, B13 | BaseAgent ABC from SKILLS.md: agent_id, state machine (SPAWNING→ACTIVE→IDLE→BLOCKED→RETIRED), heartbeat loop (30s), idle detection (5min→IDLE, 15min→RETIRE), touch() on task. AgentRegistry: spawn(), retire(), list(), get(). Max agents cap (MAX_AGENTS env, default 20). Lifecycle events → agents.lifecycle stream. | packages/agents/src/agents/base.py packages/agents/src/registry.py | ✅ State machine transitions correct ✅ Heartbeat publishes every 30s ✅ Idle detection: 5min→IDLE, 15min→RETIRE ✅ touch() resets idle timer ✅ Registry: spawn/retire/list/get work ✅ Max agents enforced (21st queued) ✅ Lifecycle events published to stream | RUN: pytest packages/agents/tests/test_base_agent.py → pass TEST: state machine all transitions TEST: heartbeat timing TEST: max agents cap | M | Not Started | RULES.md, SKILLS.md | ⚡Critical
A2 | Tool Registry + All Tools | Agents | BackendAgent | A1, B4, B5, B7, B8, B9, B10 | PG-4 (Core Logic) | A3 | ToolRegistry from SKILLS.md: register(), execute() with error handling. Implement ALL 12 tools: fetch_option_chain, compute_features, evaluate_signal, check_risk, place_order, get_order_status, get_portfolio_state, run_backtest, write_memory, read_memory, send_alert, query_strategy_registry. Each tool wraps corresponding backend service. JSON schemas for Groq function calling. | packages/agents/src/tools/registry.py packages/agents/src/tools/market_tools.py packages/agents/src/tools/trade_tools.py packages/agents/src/tools/risk_tools.py packages/agents/src/tools/portfolio_tools.py packages/agents/src/tools/memory_tools.py packages/agents/src/tools/alert_tools.py | ✅ All 12 tools registered and callable ✅ Each tool returns correct schema ✅ Error handling: tool error → {error, detail} ✅ write_memory: rejects forbidden patterns ✅ place_order: refuses without risk approval ✅ JSON schemas match SKILLS.md ✅ Tool execution logged | RUN: pytest packages/agents/tests/test_tools.py → pass TEST: each tool with valid + invalid inputs TEST: write_memory rejects credentials | L | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
A3 | Skill Library | Agents | BackendAgent | A2 | PG-5 (Integration) | A4 | All 6 skills from SKILLS.md: analyze_market_regime, generate_and_validate_signal, execute_trade_cycle, daily_performance_report, run_strategy_backtest, emergency_shutdown. Each skill = validated tool chain with validation between steps. Skills prevent wrong ordering (e.g., can't place order before risk check). | packages/agents/src/skills/registry.py packages/agents/src/skills/market_regime.py packages/agents/src/skills/signal_validation.py packages/agents/src/skills/trade_execution.py packages/agents/src/skills/daily_report.py packages/agents/src/skills/backtest_analysis.py packages/agents/src/skills/emergency_shutdown.py | ✅ All 6 skills implemented with validation ✅ analyze_market_regime: stale check → features → classify ✅ execute_trade_cycle: risk approval check enforced ✅ emergency_shutdown: cancel → halt → alert sequence ✅ Validation between steps prevents misordering ✅ Each skill has test with mock tools | RUN: pytest packages/agents/tests/test_skills.py → pass TEST: skill rejects out-of-order tool calls TEST: emergency_shutdown sequence correct | M | Not Started | RULES.md, SKILLS.md | High
A4 | Supervisor Agent | Agents | BackendAgent | A1, A2, A3 | PG-5 (Integration) | A5 | Supervisor with system prompt from blueprint. Uses Groq 70B. Lifecycle monitor (30s loop): check heartbeats, idle timeouts, spawn/retire decisions. Spawn triggers: market open, strategy activated, order approved, backtest requested. Destroy triggers: idle timeout, risk block, kill switch, crash. Routes tasks to sub-agents. Escalation: sub-agent confidence <0.6 → Supervisor takes over. | packages/agents/src/supervisor.py packages/agents/src/prompts/supervisor.py | ✅ Supervisor spawns agents on triggers ✅ Lifecycle monitor runs every 30s ✅ Idle agents retired after 15min ✅ Missed heartbeats → auto-retire ✅ Kill switch retires all instantly ✅ Escalation on low confidence works ✅ Task routing to correct sub-agent ✅ Max agents cap respected | RUN: pytest packages/agents/tests/test_supervisor.py → pass TEST: spawn on market open TEST: retire on idle TEST: escalation on confidence <0.6 | L | Not Started | RULES.md, SKILLS.md | ⚡Critical
A5 | Sub-Agent Implementations | Agents | BackendAgent | A1, A2, A4 | PG-6 (Advanced) | A6 | All 8 sub-agents with system prompts from blueprint: MarketDataAgent (regime classification), StrategyAgent (strategy suggestions), RiskAgent (risk summarization), ExecutionAgent (order workflow), PortfolioAgent (P&L commentary), PerformanceAgent (reports), AlertingAgent (alert composition), BacktestAgent (backtest summary). Each uses Groq 8B. Each handles tasks via handle_task(). | packages/agents/src/agents/market_data.py ...strategy.py, risk.py, execution.py, portfolio.py, performance.py, alerting.py, backtest.py packages/agents/src/prompts/ (8 files) | ✅ All 8 agents implemented ✅ Each has correct system prompt ✅ Each handles assigned tools only ✅ Output format matches blueprint JSON ✅ Confidence score included in output ✅ MarketDataAgent: classifies regime correctly ✅ ExecutionAgent: checks risk approval freshness ✅ Each agent has individual test file | RUN: pytest packages/agents/tests/test_agents/ → all pass TEST: each agent with mock LLM response TEST: ExecutionAgent rejects stale approval | L | Not Started | RULES.md, SKILLS.md | High
A6 | LLM Router + Groq/Ollama Clients | Agents | BackendAgent | A1 | PG-3 (Services) | A2 | ModelRouter from SKILLS.md: route() based on complexity + agent type. Groq client (8B + 70B). Ollama client (local fallback). Circuit breaker: 3 consecutive Groq errors → switch to Ollama for 5 min. Daily token budget tracking. Regime classification cache (60s TTL). Cost estimation logging. | packages/agents/src/llm/groq_client.py packages/agents/src/llm/local_client.py packages/agents/src/llm/router.py | ✅ Groq 8B calls work for sub-agents ✅ Groq 70B calls work for supervisor ✅ Ollama fallback works when Groq down ✅ Circuit breaker: 3 errors → Ollama for 5min ✅ Token budget tracked daily ✅ Cache: same regime query within 60s → cached ✅ Cost estimation in logs | RUN: pytest packages/agents/tests/test_llm.py → pass TEST: circuit breaker triggers after 3 errors TEST: cache returns same result within TTL | M | Not Started | RULES.md, SKILLS.md | High
A7 | Memory Layers | Agents | BackendAgent | A1, B2, B3 | PG-3 (Services) | A2 | WorkingMemory (Redis, TTL 5min), SessionMemory (Redis, TTL 1day), LongTermMemory (PostgreSQL). Schema validation on all writes. Forbidden pattern check (credentials, PII). From SKILLS.md patterns. Memory write rules enforced at tool level. | packages/agents/src/memory/working.py packages/agents/src/memory/session.py packages/agents/src/memory/long_term.py | ✅ Working memory: set/get with 5min TTL ✅ Session memory: append/list with 1day TTL ✅ Long-term: write/query to PostgreSQL ✅ Schema validation on all writes ✅ Forbidden patterns rejected ✅ Credential pattern → REJECTED ✅ Max value size 1MB enforced | RUN: pytest packages/agents/tests/test_memory.py → pass TEST: TTL expiry works TEST: forbidden pattern rejection | M | Not Started | RULES.md, SKILLS.md, SPECS.md | High
═══ FRONTEND WORKSTREAM · Paste into → FrontendAgent ═══
F1 | Project Scaffold + Layout Shell | Frontend | FrontendAgent | None (kickoff) | PG-1 (Kickoff) | B1, D1, Q1, P5 | Next.js 14 App Router + TS + Tailwind + shadcn/ui. Layout: left sidebar (collapsible, nav: Markets/Trade/Analytics/Alerts/Admin), top bar (logo, connection status dot, mode indicator advisory/semi-auto, kill switch button), central workspace. Dark mode toggle. Responsive: mobile sidebar → bottom nav. | packages/dashboard/package.json src/app/layout.tsx src/components/layout/Sidebar.tsx src/components/layout/TopBar.tsx src/components/layout/Workspace.tsx | ✅ Layout renders: 1920px, 768px, 375px ✅ Sidebar collapses/expands ✅ Nav between 5 sections works ✅ Dark mode toggle ✅ Kill switch button visible in top bar ✅ Mode indicator: Advisory/Semi-Auto ✅ Connection status dot placeholder | RUN: npm run dev → localhost:3000 RUN: npm run lint → 0 errors RUN: npm run build → success VISUAL: check 3 breakpoints | M | Not Started | RULES.md, WORKFLOW.md | ⚡Critical
F2 | API Client + WebSocket Hook | Frontend | FrontendAgent | F1 | PG-2 (Foundation) | F8, F9 | Typed fetch wrapper (api.ts): error handling, auth header, base URL. useWebSocket hook: auto-reconnect (exponential backoff), channel subscription, connection status enum. Update TopBar connection dot. MSW setup for API mocking in tests. | src/lib/api.ts src/lib/ws.ts src/hooks/useWebSocket.ts | ✅ API client: GET/POST/PUT/DELETE typed ✅ Handles 401 → redirect, 500 → error toast ✅ WebSocket: connect, subscribe, auto-reconnect ✅ Connection status in TopBar (green/yellow/red) ✅ TypeScript strict: no 'any' ✅ MSW handlers for test mocking | RUN: vitest tests/hooks/ → pass RUN: npm run typecheck → 0 errors TEST: mock API calls via MSW | M | Not Started | RULES.md, SPECS.md | ⚡Critical
F2a | Onboarding Wizard | Frontend | FrontendAgent | F1, F2, B15 | PG-4 (Integration) | F3 | 4-step onboarding wizard for first-time users: Step 1 — Connect Broker (dropdown: Paper Trading / Dhan; if Dhan: API key + secret inputs; also crypto exchange toggle: Binance/Bybit + keys). Step 2 — Risk Profile (sliders/inputs: max daily loss, max drawdown %, max position size, max margin %). Step 3 — Choose Strategies (cards with backtest metrics, toggle ON/OFF, param editor expandable). Step 4 — Choose Instruments (NIFTY/BANKNIFTY checkboxes + crypto pairs if crypto enabled). Progress indicator. Skip = paper trading defaults. Saves via /onboarding/* API endpoints. | src/app/onboarding/page.tsx src/components/onboarding/BrokerStep.tsx src/components/onboarding/RiskStep.tsx src/components/onboarding/StrategyStep.tsx src/components/onboarding/InstrumentStep.tsx src/components/onboarding/WizardProgress.tsx | ✅ 4 steps render with progress indicator ✅ Step 1: Paper/Dhan/Crypto selector works ✅ Step 1: Dhan shows API key fields (masked input) ✅ Step 1: validates broker connection via API ✅ Step 2: sliders set risk params with defaults ✅ Step 3: strategy cards show backtest metrics ✅ Step 4: instrument selection persists ✅ Skip → paper trading with defaults ✅ Completion → redirects to dashboard ✅ Returns to incomplete step on revisit | RUN: vitest tests/onboarding/ → pass VISUAL: walk through all 4 steps TEST: skip → defaults applied TEST: API calls on each step completion | L | Not Started | RULES.md, SPECS.md | High
F3 | Markets Module | Frontend | FrontendAgent | F2, B4 | PG-3 (Modules) | F4, F5 | Option chain table (strikes × CE/PE with LTP, OI, IV, Greeks). ITM shading. IV chart (Recharts). OI chart (bar). Regime badge. Asset class toggle: Equity / Crypto (shows crypto orderbook view when crypto selected). Real-time via WebSocket. Loading/error/empty states. | src/app/markets/page.tsx src/components/markets/OptionChainTable.tsx src/components/markets/CryptoOrderbook.tsx src/components/markets/IVChart.tsx src/components/markets/OIChart.tsx src/components/markets/RegimeBadge.tsx | ✅ Option chain renders all columns ✅ ITM strikes shaded ✅ IV + OI charts render ✅ Regime badge updates via WS ✅ Equity/Crypto toggle switches view ✅ Crypto: orderbook depth visualization ✅ Loading/error/empty states ✅ Real-time updates | RUN: vitest tests/markets/ → pass VISUAL: charts + table with mock data TEST: asset class toggle switches view | L | Not Started | RULES.md, SPECS.md | High
F4 | Trade Module | Frontend | FrontendAgent | F2, B6, B9 | PG-3 (Modules) | F3, F5 | Active signals list with risk status (green✓/red✗). Signal detail card. Order form pre-filled from signal (editable). Position table with live P&L (green/red). Order history (filterable). Advisory mode: 'Execute' button on signal. Semi-auto mode: signal shows 'Auto-executing in 5s' with cancel button. Asset class indicator on each signal/position. | src/app/trade/page.tsx src/components/trade/SignalCard.tsx src/components/trade/OrderForm.tsx src/components/trade/PositionTable.tsx src/components/trade/OrderHistory.tsx | ✅ Signal cards show risk approval status ✅ Order form validates (qty>0, price>0) ✅ Pre-fills from signal ✅ P&L colored: green/red ✅ Order history filterable ✅ Advisory: Execute button present ✅ Semi-auto: countdown + cancel ✅ Asset class indicator (equity/crypto badge) | RUN: vitest tests/trade/ → pass VISUAL: signal → order → position flow TEST: mode-specific UI behavior | L | Not Started | RULES.md, SPECS.md | High
F5 | Analytics Module | Frontend | FrontendAgent | F2, B10, B14 | PG-3 (Modules) | F3, F4 | P&L chart (area: daily/cumulative). Drawdown chart. Regime timeline. Strategy performance table (sortable). Win/loss histogram. Date range selector. Backtest panel: configure + run + results view (equity curve, metrics, LLM summary). Asset class filter: All/Equity/Crypto. Export CSV. | src/app/analytics/page.tsx src/components/analytics/PnLChart.tsx src/components/analytics/BacktestPanel.tsx src/components/analytics/StrategyTable.tsx src/components/analytics/DrawdownChart.tsx src/components/analytics/RegimeTimeline.tsx | ✅ P&L daily + cumulative toggle ✅ Drawdown inverted area chart ✅ Regime timeline colored segments ✅ Strategy table sortable ✅ Date range: 1D/1W/1M/3M/Custom ✅ Backtest: config → run → results ✅ Asset class filter works ✅ Export CSV button ✅ Charts responsive | RUN: vitest tests/analytics/ → pass VISUAL: all charts + backtest flow TEST: date range updates charts | L | Not Started | RULES.md, SPECS.md | Medium
F6 | Alerts Module | Frontend | FrontendAgent | F2, B3 | PG-4 (Integration) | F7 | Alert feed (real-time WS). Severity colors (INFO=blue, WARNING=orange, CRITICAL=red pulsing). Alert config panel: thresholds, channels. Alert history with severity+date filters. Notification sound for CRITICAL (configurable off). | src/app/alerts/page.tsx src/components/alerts/AlertFeed.tsx src/components/alerts/AlertConfig.tsx src/components/alerts/AlertHistory.tsx | ✅ Alerts appear instantly via WS ✅ Severity colors correct ✅ CRITICAL pulses ✅ Config saves persist via API ✅ History filterable ✅ Sound for CRITICAL (toggle off) | RUN: vitest tests/alerts/ → pass TEST: mock alert → appears in feed | M | Not Started | RULES.md, SPECS.md | Medium
F7 | Admin Module | Frontend | FrontendAgent | F2, B12 | PG-4 (Integration) | F6 | Kill switch: big red button → TWO-STEP confirm (dialog with flatten checkbox). Agent monitor: table with live heartbeat indicator. Strategy manager: activate/deactivate + params editor. System config viewer. Mode toggle: Advisory ↔ Semi-Auto. Post-killswitch: 'SYSTEM HALTED' banner + reset button. | src/app/admin/page.tsx src/components/admin/KillSwitch.tsx src/components/admin/AgentMonitor.tsx src/components/admin/StrategyManager.tsx src/components/admin/ModeToggle.tsx | ✅ Kill switch: TWO clicks required ✅ Confirm dialog shows flatten checkbox ✅ Agent table updates live ✅ Strategy toggle works ✅ Mode toggle: Advisory ↔ Semi-Auto ✅ Post-killswitch: SYSTEM HALTED banner ✅ Reset button re-enables | RUN: vitest tests/admin/ → pass VISUAL: kill switch flow TEST: agent table refresh on lifecycle events | M | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
F8 | Shared Components | Frontend | FrontendAgent | F1 | PG-2 (Foundation) | B2, B3, F2 | DataTable (sort, filter, paginate), MetricCard (value + trend arrow), StatusBadge (colored pill), AssetClassBadge (equity green, crypto purple), LoadingSpinner, ErrorBoundary, ConfirmDialog, Toast system. All responsive + dark mode + ARIA. | src/components/shared/ | ✅ DataTable: sort, filter, paginate ✅ MetricCard: value + trend ✅ All components responsive ✅ All have ARIA labels ✅ Dark mode compatible ✅ AssetClassBadge: equity/crypto ✅ Each has test file | RUN: vitest tests/shared/ → pass VISUAL: each component in isolation | M | Not Started | RULES.md | High
F9 | State Management | Frontend | FrontendAgent | F2 | PG-2 (Foundation) | F8 | Zustand stores: portfolioStore, signalStore, agentStore, configStore. React Query: server state + WS invalidation. Optimistic updates for orders. Multi-asset: portfolio store handles equity + crypto positions separately + combined. | src/lib/stores/ src/hooks/useMarketData.ts src/hooks/usePortfolio.ts | ✅ Stores update on WS events ✅ React Query cache invalidated on WS ✅ Optimistic order update + revert on fail ✅ Stale data indicators (30s warning) ✅ Multi-asset portfolio separation ✅ Persistence across navigation | RUN: vitest tests/hooks/ → pass TEST: WS → store → component flow | M | Not Started | RULES.md, SPECS.md | High
F10 | Real-Time Integration + Polish | Frontend | FrontendAgent | F3, F4, F5, F6, F7 | PG-5 (Polish) | F11 | Connect ALL modules to live WS. Throttle to 10 updates/sec. Virtualize long lists (react-window). Disconnect → 'Reconnecting' banner + auto-reconnect. No stale data after reconnect. | All module pages + hooks | ✅ 10 updates/sec no frame drops ✅ Long lists virtualized ✅ Disconnect → banner → reconnect ✅ No stale data after reconnect ✅ Memory stable over 1 hour | RUN: vitest integration tests → pass PERF: Chrome DevTools no frame drops TEST: disconnect → reconnect → data resumes | M | Not Started | RULES.md | High
F11 | Responsive Design | Frontend | FrontendAgent | F3, F4, F5, F6, F7 | PG-5 (Polish) | F10 | All modules work at 768px and 375px. Charts resize. Touch targets ≥44px. Bottom nav on mobile. Kill switch accessible on mobile. | All component files | ✅ All 5 modules usable at 768/375px ✅ No horizontal scroll ✅ Touch targets ≥44px ✅ Charts readable on mobile ✅ Kill switch on mobile top bar | VISUAL: test 1920, 768, 375 RUN: Lighthouse accessibility → 90+ | M | Not Started | RULES.md | Medium
F12 | Frontend Test Suite | Frontend | FrontendAgent | F3–F9 | PG-6 (Validation) | Q5 | Component tests (RTL + vitest). Hook tests. Integration tests (MSW). ≥80% coverage. Critical flows: order placement, kill switch, onboarding wizard, alert config, WS reconnect, backtest, mode toggle. | packages/dashboard/tests/ | ✅ Coverage ≥80% ✅ Order flow tested ✅ Kill switch flow tested ✅ Onboarding wizard tested ✅ Mode toggle tested ✅ WS reconnect tested ✅ No console.error in tests | RUN: vitest --coverage → ≥80% RUN: vitest → all pass | M | Not Started | RULES.md, WORKFLOW.md | High
═══ QA WORKSTREAM · Paste into → QAAgent ═══
Q1 | Test Strategy & Fixtures | QA | QAAgent | None (kickoff) | PG-1 (Kickoff) | B1, F1, D1, P5 | Test strategy document. Fixtures in data/fixtures/: sample_option_chain.json (NIFTY+BANKNIFTY), sample_crypto_orderbook.json, sample_feature_vector.json, sample_signals.json, sample_portfolio.json (equity+crypto), sample_risk_params.json. All validate against SPECS.md Pydantic models. | data/fixtures/ (7+ files) docs/test-strategy.md | ✅ Test strategy covers all types ✅ 7+ fixture files ✅ All validate against Pydantic models ✅ Cover: happy, boundary, error cases ✅ Crypto fixtures included ✅ README explains each file | RUN: python tests/validate_fixtures.py → valid REVIEW: test-strategy.md is actionable | S | Not Started | RULES.md, SPECS.md, SKILLS.md | ⚡Critical
Q2 | Risk Engine Fuzz Testing | QA | QAAgent | B7 | PG-5 (Validation) | Q3 | Hypothesis property-based testing for ALL 10 risk rules. Boundary: exact limits, ±1, extreme values (0, negative, MAX_FLOAT). Time boundaries with timezone. Crypto-specific: leverage limits, always-open time check. Prove: no input combination bypasses risk. | tests/test_risk_engine_fuzz.py | ✅ 1000+ generated cases pass ✅ Boundary tests all 10 rules ✅ No bypass found ✅ Crypto: leverage + always-open tested ✅ Edge cases documented | RUN: pytest tests/test_risk_engine_fuzz.py → pass CHECK: hypothesis stats → 1000+ examples | M | Not Started | RULES.md, SPECS.md | ⚡Critical
Q3 | Signal Engine Validation | QA | QAAgent | B6, Q1 | PG-5 (Validation) | Q2 | 10+ reference scenarios for all 3 strategies (Iron Condor, Momentum, SMC). Test: correct signals, wrong regime → NO_SIGNAL, missing features → error. Crypto strategy scenarios included. | tests/test_signal_validation.py | ✅ 10+ scenarios all correct ✅ Wrong regime → NO_SIGNAL ✅ Missing features → error (not crash) ✅ SMC: order block + FVG confluence tested ✅ Crypto scenarios included | RUN: pytest tests/test_signal_validation.py → pass | M | Not Started | RULES.md, SPECS.md, SKILLS.md | High
Q4 | Agent Lifecycle Integration Tests | QA | QAAgent | A4, A5, B16 | PG-6 (Agent Tests) | Q5 | Test: spawn→active→task→idle→retire. Tool calling outputs. Memory schema compliance. Error → no crash. Heartbeat timeout → retire. Kill switch → all retire. Supervisor spawn/destroy decisions correct. | packages/agents/tests/test_lifecycle.py | ✅ Full lifecycle tested ✅ Tool outputs correct ✅ Memory writes valid ✅ Errors don't crash agent ✅ Heartbeat timeout → retire ✅ Kill switch → all retire <2s ✅ No dangling agents after teardown | RUN: pytest tests/test_lifecycle.py → pass | L | Not Started | RULES.md, SKILLS.md | High
Q5 | End-to-End Trading Cycle | QA | QAAgent | B16, F10 | PG-7 (E2E) | Q6 | Full E2E: (1) equity cycle tick→signal→risk→order→fill→portfolio→dashboard, (2) crypto cycle same flow, (3) Dhan adapter mock cycle. <10 seconds each. Audit trail complete. Correlation ID traceable through all steps. | tests/e2e/test_full_cycle.py | ✅ Equity cycle <10s ✅ Crypto cycle <10s ✅ Dhan mock cycle passes ✅ Dashboard WS receives all events ✅ Audit trail complete (9 steps) ✅ Correlation ID end-to-end | RUN: pytest tests/e2e/ → all pass | L | Not Started | RULES.md, WORKFLOW.md, SPECS.md, SKILLS.md | ⚡Critical
Q6 | Kill Switch E2E | QA | QAAgent | B12, F7 | PG-7 (E2E) | Q5 | Kill switch from: API, dashboard, (Telegram placeholder). Verify: all pending cancelled across ALL broker adapters (paper+dhan+crypto), agents stopped, system.killswitch published, CRITICAL alert, system locked, reset re-enables. | tests/e2e/test_killswitch.py | ✅ API kill switch <2s ✅ Dashboard button triggers ✅ All brokers: orders cancelled ✅ Post-killswitch: 423 on new orders ✅ Reset re-enables ✅ CRITICAL alert sent ✅ Audit log recorded | RUN: pytest tests/e2e/test_killswitch.py → pass | M | Not Started | RULES.md, SKILLS.md | ⚡Critical
Q7 | Load Testing | QA | QAAgent | B16, F10 | PG-8 (Stress) | Q8 | 100 ticks/sec × 5min. 10 concurrent agents. 10 WS clients. 50 orders/min. Memory stable. p95 latency <2s. No data loss. Multi-asset: equity + crypto simultaneous. | tests/load/ | ✅ 100 ticks/sec sustained ✅ Memory stable (<10% growth) ✅ Agent latency <2s p95 ✅ WS delivery <200ms p95 ✅ No data loss ✅ Multi-asset simultaneous | RUN: python tests/load/run.py → report CHECK: all metrics pass | L | Not Started | RULES.md | Medium
Q8 | Security Audit | QA | QAAgent | B13, B1 | PG-8 (Stress) | Q7 | No credentials in logs (grep test). Auth on all endpoints (401 test). Rate limiting (429 test). SQL injection (Pydantic blocks). WebSocket auth. CORS. Input validation (oversized → 413). Dhan + crypto credentials specifically checked. | tests/security/ docs/security-checklist.md | ✅ Zero credential patterns in logs ✅ All endpoints 401 without auth ✅ Rate limiting 429 enforced ✅ SQL injection blocked ✅ WS rejects without token ✅ CORS blocks unauthorized ✅ Dhan/crypto keys not leaked | RUN: pytest tests/security/ → pass RUN: grep 'DHAN\¦CRYPTO.*KEY' logs/ → 0 | M | Not Started | RULES.md | High
═══ DEVOPS WORKSTREAM · Paste into → DevOpsAgent ═══
D1 | Docker Setup | DevOps | DevOpsAgent | None (kickoff) | PG-1 (Kickoff) | B1, F1, Q1, P5 | Dockerfiles: api (Python 3.11), dashboard (Node 20, multi-stage), agents (Python 3.11). docker-compose.dev.yml: api (hot reload), dashboard (next dev), redis, postgres (init script), mock-broker. Health checks on all. Starts with 'docker compose up'. | infra/docker/Dockerfile.api infra/docker/Dockerfile.dashboard infra/docker/Dockerfile.agents docker-compose.dev.yml | ✅ docker compose up → all 5 services healthy ✅ Health checks pass <30s ✅ Hot reload: api + dashboard ✅ Postgres initialized with trading DB ✅ .env.example loaded ✅ docker compose down cleans up | RUN: docker compose up -d → healthy RUN: curl localhost:8000/health → 200 RUN: curl localhost:3000 → 200 | M | Not Started | RULES.md, WORKFLOW.md | ⚡Critical
D2 | CI Pipeline | DevOps | DevOpsAgent | D1 | PG-2 (CI/CD) | D3 | GitHub Actions ci.yml: lint (ruff+eslint parallel), typecheck (mypy+tsc parallel), tests (pytest+vitest parallel), build (docker build ×3), security (bandit+npm audit). On every PR. <5 min total. Fail fast on lint. | .github/workflows/ci.yml | ✅ Triggers on PR ✅ Lint parallel ✅ Typecheck parallel ✅ Tests with coverage ✅ Docker builds ✅ Security scan ✅ <5 min total ✅ Fail fast on lint | RUN: push branch → CI triggers TEST: lint error → fast fail | M | Not Started | RULES.md, WORKFLOW.md | High
D3 | DB Migration Pipeline | DevOps | DevOpsAgent | B2, D2 | PG-2 (CI/CD) | D2 | Alembic in CI: up → verify → down on test DB. migrate.sh: check pending → backup → upgrade → verify. Rollback script. | .github/workflows/ci.yml (migration job) infra/scripts/migrate.sh | ✅ CI migration up+down passes ✅ migrate.sh works ✅ Rollback works ✅ Failure → CI fails | RUN: migrate.sh → success RUN: migrate.sh rollback → success | S | Not Started | RULES.md, WORKFLOW.md | Medium
D4 | Staging Environment | DevOps | DevOpsAgent | D1 | PG-3 (Environments) | D5 | docker-compose.stg.yml: 2 API replicas, dashboard, redis (persist), postgres (volume), agents, prometheus, grafana. Paper + Dhan sandbox mode. | docker-compose.stg.yml | ✅ All services + monitoring start ✅ 2 API replicas ✅ Data persists restart ✅ Prometheus scrapes all ✅ Grafana on :3001 | RUN: docker compose -f stg.yml up → healthy CHECK: prometheus targets UP | M | Not Started | RULES.md, WORKFLOW.md | Medium
D5 | Secrets Management | DevOps | DevOpsAgent | D1 | PG-3 (Environments) | D4 | .env.example with ALL keys (paper+dhan+crypto). .gitignore. Pre-commit hook (detect-secrets). Docker images clean. Vault/SOPS doc for prod. | .env.example .gitignore .pre-commit-config.yaml docs/secrets.md | ✅ .env.example complete (all adapters) ✅ Pre-commit detects secrets ✅ Docker images clean ✅ Setup documented ✅ Git history clean | RUN: pre-commit run --all → pass RUN: docker inspect → no secrets | S | Not Started | RULES.md, WORKFLOW.md | High
D6 | Monitoring & Alerting | DevOps | DevOpsAgent | D4, B13 | PG-4 (Observability) | D7 | 4 Grafana dashboards: Trading (P&L, signals, orders), Agents (count, latency, errors), System (CPU, mem, Redis, Postgres, API latency), LLM (calls, tokens, cost). Prometheus alert rules: agent down, risk error, kill switch, high latency. Multi-asset metrics (equity vs crypto breakdown). | infra/monitoring/ | ✅ 4 dashboards created ✅ Multi-asset breakdown ✅ Alert rules fire correctly ✅ Alerts routed correctly | RUN: Grafana → 4 dashboards render TEST: mock alert fires | M | Not Started | RULES.md, WORKFLOW.md | Medium
D7 | Production K8s Config | DevOps | DevOpsAgent | D4 | PG-5 (Prod) | D8 | K8s manifests: API (3 replicas, HPA), agents (2 replicas), Redis StatefulSet, Postgres StatefulSet. Resource limits. Probes. Rolling update. Network policies. | infra/k8s/ | ✅ dry-run succeeds ✅ Resource limits set ✅ Probes configured ✅ HPA: 3→6 at 70% CPU ✅ Network policies | RUN: kubectl apply --dry-run → success | L | Not Started | RULES.md, WORKFLOW.md | Medium
D8 | DR & Backup | DevOps | DevOpsAgent | D4 | PG-5 (Prod) | D7 | Daily pg_dump. Redis RDB snapshots. Restore script. Recovery runbook. Backup → destroy → restore test. RTO <1hr, RPO <24hr. | infra/scripts/backup.sh infra/scripts/restore.sh docs/runbook.md (DR section) | ✅ Backup produces valid dump ✅ Restore recovers full DB ✅ Redis snapshot configured ✅ Runbook DR section complete ✅ Tested: backup→destroy→restore | RUN: backup.sh → .sql.gz RUN: restore.sh → success | M | Not Started | RULES.md, WORKFLOW.md | Medium
═══ DOCS WORKSTREAM · Paste into → DocsAgent ═══
P1 | Architecture Documentation | Docs | DocsAgent | B1, B3 | PG-3 (Docs) | P2 | Full system architecture: components, data flow, deployment, agents, tools, memory. ASCII diagram. Multi-asset notes (equity + crypto). Dhan adapter documentation. Target: new developer. | docs/architecture.md | ✅ All sections covered ✅ Diagram included ✅ Multi-asset documented ✅ Dhan adapter noted ✅ Readable for newcomers | REVIEW: complete, no TODOs | M | Not Started | RULES.md, WORKFLOW.md, SPECS.md, SKILLS.md | Medium
P2 | API Reference | Docs | DocsAgent | B1, B11 | PG-3 (Docs) | P1 | OpenAPI supplement: examples for each endpoint (curl), WebSocket protocol, auth guide, rate limits, onboarding flow, multi-broker error codes. | docs/api-reference.md | ✅ All endpoints with curl examples ✅ WS protocol documented ✅ Auth flow documented ✅ Onboarding endpoints documented ✅ Dhan + crypto error codes | REVIEW: complete TEST: curl examples work | S | Not Started | SPECS.md | Medium
P3 | Agent Design Guide | Docs | DocsAgent | A4, A5 | PG-4 (Docs) | P4 | Agent roster, lifecycle state machine, prompts, tool-use rules, memory rules, model routing. 'How to Add a New Agent' step-by-step. 'How to Add a New Strategy' step-by-step. | docs/agent-design.md | ✅ All 9 agents documented ✅ Lifecycle diagram ✅ Add New Agent guide ✅ Add New Strategy guide ✅ Memory rules stated | REVIEW: guides are actionable | M | Not Started | RULES.md, SKILLS.md | Medium
P4 | Operations Runbook | Docs | DocsAgent | D4, D8 | PG-5 (Docs) | P3 | 6 procedures: deployment, kill switch, add strategy, add broker adapter (Dhan/crypto), troubleshooting (10+ issues), DR. Dhan-specific troubleshooting: token refresh, rate limits. | docs/runbook.md | ✅ All 6 procedures step-by-step ✅ Kill switch decision tree ✅ Dhan troubleshooting ✅ Crypto adapter troubleshooting ✅ 10+ common issues | REVIEW: followable by someone unfamiliar | M | Not Started | RULES.md, WORKFLOW.md, SKILLS.md | Medium
P5 | Developer Onboarding | Docs | DocsAgent | D1 | PG-1 (Kickoff) | B1, F1, D1, Q1 | Getting started: prerequisites, clone+setup (3 commands), run locally, verify, project structure, where to find things. CONTRIBUTING.md with PR process. | docs/getting-started.md CONTRIBUTING.md | ✅ Setup in <5 minutes ✅ 3 commands to running ✅ Health check verification ✅ Project structure reference ✅ PR template in CONTRIBUTING.md | TEST: fresh Docker machine → follow guide → running | S | Not Started | WORKFLOW.md | High

## Dependency Map
Task | Title | Depends On | Blocks | Parallel Group | Critical Path? | Earliest Start
B1 | Project Scaffold | None | B2,B3,B4,B8,B11,B13,B15 | PG-1 | YES | Day 1
B2 | DB Models | B1 | B6,B7,B9,B10,A1 | PG-2 | YES | After B1
B3 | Event Bus | B1 | B4,B11,B12,A1 | PG-2 | YES | After B1
B4 | Market Data | B1,B3 | B5 | PG-3 | NO | After B1+B3
B4a | Dhan Adapter | B2,B3,B8 | B9,B16 | PG-3 | NO | After B2+B3+B8
B4b | Crypto Adapter | B2,B3,B8 | B9,B16 | PG-3 | NO | After B2+B3+B8
B5 | Features | B4 | B6,B14 | PG-3 | NO | After B4
B6 | Signal+Strategy | B5,B2 | B7,B14,Q3 | PG-4 | YES | After B5+B2
B7 | Risk Engine | B2,B6 | B9,B14,Q2 | PG-4 | YES | After B2+B6
B8 | Paper Broker | B2,B3 | B4a,B4b,B9,B10 | PG-3 | NO | After B2+B3
B9 | Exec Gateway | B7,B8 | B12,B16 | PG-5 | YES | After B7+B8
B10 | Portfolio Mgr | B4,B8,B2 | B16 | PG-5 | NO | After B4+B8+B2
B11 | WebSocket | B3,B1 | F10,P2 | PG-3 | NO | After B3+B1
B12 | Kill Switch | B3,B9 | Q6 | PG-5 | YES | After B3+B9
B13 | Audit | B2,B1 | Q8,D6 | PG-2 | NO | After B2+B1
B14 | Backtest | B5,B6,B7 | B16 | PG-6 | NO | After B5+B6+B7
B15 | Onboarding API | B4,B8,B4a,B4b,B6,B7 | F2a,B16 | PG-6 | NO | After adapters+strategies
B16 | Integration Tests | B4–B15 | Q5 | PG-7 | YES | After all B tasks
A1 | Agent Base | B1,B3 | A2,A4,A6,A7 | PG-2 | YES | After B1+B3
A2 | Tool Registry | A1,B services | A3 | PG-4 | YES | After A1+B services
A3 | Skill Library | A2 | A4 | PG-5 | NO | After A2
A4 | Supervisor | A1,A2,A3 | A5,Q4 | PG-5 | YES | After A1+A2+A3
A5 | Sub-Agents | A1,A2,A4 | Q4 | PG-6 | NO | After A4
A6 | LLM Router | A1 | A2 | PG-3 | NO | After A1
A7 | Memory Layers | A1,B2,B3 | A2 | PG-3 | NO | After A1+B2+B3
F1 | Layout Shell | None | F2,F8 | PG-1 | YES | Day 1
F2 | API+WS Hook | F1 | F2a,F3–F7,F9 | PG-2 | YES | After F1
F2a | Onboarding Wizard | F1,F2,B15 | F3 | PG-4 | NO | After F2+B15
F3 | Markets | F2,B4 | F10,F11 | PG-3 | NO | After F2+B4
F4 | Trade | F2,B6,B9 | F10,F11 | PG-3 | NO | After F2+B6+B9
F5 | Analytics | F2,B10,B14 | F10,F11 | PG-3 | NO | After F2+B10+B14
F6 | Alerts | F2,B3 | F10 | PG-4 | NO | After F2+B3
F7 | Admin | F2,B12 | Q6 | PG-4 | YES | After F2+B12
F8 | Shared Comp | F1 | F3–F7 | PG-2 | NO | After F1
F9 | State Mgmt | F2 | F10 | PG-2 | NO | After F2
F10 | RT Integration | F3–F7 | Q5 | PG-5 | NO | After all modules
F11 | Responsive | F3–F7 | F12 | PG-5 | NO | After all modules
F12 | FE Tests | F3–F9 | — | PG-6 | NO | After all FE code
Q1 | Fixtures | None | Q2,Q3 | PG-1 | YES | Day 1
Q2 | Risk Fuzz | B7 | — | PG-5 | YES | After B7
Q3 | Signal Valid | B6,Q1 | — | PG-5 | NO | After B6+Q1
Q4 | Agent Tests | A4,A5,B16 | Q5 | PG-6 | NO | After agents+B16
Q5 | E2E Cycle | B16,F10 | — | PG-7 | YES | After B16+F10
Q6 | Kill Switch E2E | B12,F7 | — | PG-7 | YES | After B12+F7
Q7 | Load Test | B16,F10 | — | PG-8 | NO | After B16+F10
Q8 | Security | B13,B1 | — | PG-8 | NO | After B13+B1
D1 | Docker | None | D2,D4,D5 | PG-1 | YES | Day 1
D2 | CI | D1 | D3 | PG-2 | NO | After D1
D3 | DB Migrations CI | B2,D2 | — | PG-2 | NO | After B2+D2
D4 | Staging | D1 | D6,D7,D8 | PG-3 | NO | After D1
D5 | Secrets | D1 | — | PG-3 | NO | After D1
D6 | Monitoring | D4,B13 | — | PG-4 | NO | After D4+B13
D7 | Prod K8s | D4 | — | PG-5 | NO | After D4
D8 | DR+Backup | D4 | P4 | PG-5 | NO | After D4
P1 | Architecture | B1,B3 | — | PG-3 | NO | After B1+B3
P2 | API Ref | B1,B11 | — | PG-3 | NO | After B1+B11
P3 | Agent Guide | A4,A5 | — | PG-4 | NO | After agents done
P4 | Runbook | D4,D8 | — | PG-5 | NO | After D4+D8
P5 | Onboarding | D1 | — | PG-1 | NO | After D1

## Parallel Execution
Parallel Group | Tasks | All Start Together? | Prerequisites | Agents In Parallel | Key Notes
PG-1 (Kickoff) | B1, F1, D1, Q1, P5 | ✅ YES All Day 1 | None | Backend + Frontend + DevOps + QA + Docs (5 agents parallel) | MAXIMUM parallelism. Zero dependencies. Start ALL immediately. 5 independent workstreams.
PG-2 (Foundation) | B2, B3, B13, A1, F2, F8, F9, D2, D3 | ✅ YES after PG-1 | PG-1 complete | Backend + Frontend + DevOps (3 agents) | Foundation layers. Backend: DB + Events + Agent base. Frontend: API client + components. DevOps: CI pipeline.
PG-3 (Services) | B4, B4a, B4b, B5, B8, B11, A6, A7, F3, F4, F5, D4, D5, P1, P2 | ⚠️ PARTIAL see deps | PG-2 relevant | All 5 agents (highest parallelism) | HIGHEST task count (15). B4/B4a/B4b/B8/B11 can start together. F3 needs B4. Dhan + Crypto adapters parallel with each other.
PG-4 (Core Logic) | B6, B7, A2, F2a, F6, F7, D6, P3 | ⚠️ PARTIAL B6→B7 sequential | B5+B2 for B6; B6 for B7 | Backend (CRITICAL) + Frontend + DevOps + Docs | ⚠️ B6→B7 is THE critical path. Frontend F6/F7 and onboarding wizard can proceed in parallel.
PG-5 (Integration) | B9, B10, B12, A3, A4, F10, F11, D7, D8, P4, Q2 | ⚠️ PARTIAL | Risk+Exec ready | All agents | Integration layer. B9 needs B7+B8. Kill switch needs B9. Agent skills + supervisor built here.
PG-6 (Advanced) | B14, B15, A5, F12, Q3, Q4 | ⚠️ PARTIAL | Core done | Backend + Frontend + QA | Backtest runner, onboarding API, sub-agents, test suites. All can run in parallel.
PG-7 (Validation) | B16, Q5, Q6 | ⚠️ PARTIAL | Most B+F done | Backend + QA | Integration tests + E2E tests + kill switch E2E. B16 should complete before Q5.
PG-8 (Hardening) | Q7, Q8 | ✅ YES after PG-7 | PG-7 complete | QA only | Load testing + security audit. Can run in parallel. Final quality gate.

## Context Files Guide
Context File | When to Attach | Contains | Used By Tasks
RULES.md | EVERY task — always paste this | Iron rules (LLM never touches money, RiskEngine veto, etc), code standards (Python/TS), risk rules table (10 rules), memory rules (allowed/forbidden), error handling patterns, testing requirements | ALL tasks (B1–P5)
WORKFLOW.md | Tasks involving multi-file changes, CI/CD, cross-service work, PR creation | Git workflow (branch naming, commits, PR process), project structure quick reference, env vars list, service communication map, data flow diagram, review gates, definition of done | B1,B2,B3,B15,B16,F1,F12,D1–D8,P5,Q5
SPECS.md | Tasks involving API, database, schemas, data contracts, event streams | Database schemas (6 tables), Pydantic models (all request/response), Redis stream names+formats, WebSocket protocol, EventBus interface, BrokerAdapter interface, DataVendorAdapter interface | B2,B4,B4a,B4b,B5,B6,B7,B8,B9,B10,B11,B13,B15,F2,F3,F4,F5,Q1,Q3,Q5,P1,P2
SKILLS.md | Tasks involving agents, tools, skills, LLM integration, memory | Tool catalog (12 tools with schemas), skill library (6 skills with validation), agent base class pattern, memory layer patterns, model router logic, JSON schemas for Groq function calling | B3,B6,B7,B9,B12,A1–A7,Q1,Q2,Q3,Q4,Q5,Q6,F7,P1,P3,P4

## Agent Assignment
Antigravity Agent | Total Tasks | Task IDs | Context Files Always Needed | Agent System Prompt Summary
BackendAgent | 24 | B1,B2,B3,B4,B4a,B4b,B5,B6,B7,B8,B9,B10,B11,B12,B13,B14,B15,B16,A1,A2,A3,A4,A5,A6,A7 | RULES.md + SPECS.md + SKILLS.md | Builds FastAPI services, broker adapters (Paper+Dhan+Crypto), risk engine, signal engine, execution gateway, agent runtime, tool registry, supervisor + sub-agents, memory layers. Python 3.11, async-first, Pydantic strict.
FrontendAgent | 13 | F1,F2,F2a,F3,F4,F5,F6,F7,F8,F9,F10,F11,F12 | RULES.md + SPECS.md | Builds Next.js dashboard: onboarding wizard, markets, trade, analytics, alerts, admin modules. TypeScript strict, Tailwind+shadcn, Zustand+React Query, WebSocket integration. Multi-asset UI (equity+crypto toggle).
QAAgent | 8 | Q1,Q2,Q3,Q4,Q5,Q6,Q7,Q8 | RULES.md + SPECS.md + SKILLS.md | Test strategy, fixtures, risk fuzz testing (Hypothesis), signal validation, agent lifecycle tests, E2E trading cycles (equity+crypto+Dhan), kill switch E2E, load testing, security audit.
DevOpsAgent | 8 | D1,D2,D3,D4,D5,D6,D7,D8 | RULES.md + WORKFLOW.md | Docker setup, CI/CD pipeline (GitHub Actions), staging environment, secrets management (Dhan+crypto keys), monitoring (Grafana 4 dashboards), production K8s, DR+backup.
DocsAgent | 5 | P1,P2,P3,P4,P5 | WORKFLOW.md + SPECS.md + SKILLS.md | Architecture docs, API reference, agent design guide (incl add-new-strategy), operations runbook (incl Dhan+crypto troubleshooting), developer onboarding.
TOTAL | 0

## Critical Path
Step | Task | Title | Why Critical | Blocks
1 | B1 | Project Scaffold | Everything depends on FastAPI being initialized | B2,B3,B4,B8,B11,B13 + all downstream
2 | B2 | DB Models | Strategies, risk, portfolio all need DB tables | B6,B7,B9,B10,A1
3 | B3 | Event Bus | All inter-service communication flows through Redis Streams | B4,B11,B12,A1
4 | B5 | Features | Signal engine needs computed features to generate signals | B6
5 | B6 | Signal Engine | Risk engine validates signals; no signals = nothing to risk-check | B7,Q3
6 | B7 | Risk Engine | Execution gateway requires risk approval; THE safety gate | B9,Q2
7 | B9 | Execution Gateway | Kill switch and integration tests need order placement | B12,B16
8 | B12 | Kill Switch | Safety-critical; E2E tests depend on it | Q6
9 | A1 | Agent Base | All agents inherit from base; registry needed for supervisor | A2,A4
10 | A2 | Tool Registry | Supervisor and all agents need tools to function | A3,A4
11 | A4 | Supervisor | Orchestrates everything; agent tests depend on it | A5,Q4
12 | B16 | Integration Tests | E2E tests and QA depend on backend being fully integrated | Q5
13 | F1 | Layout Shell | All frontend modules built inside this shell | F2,F8
14 | F2 | API+WS Hook | All modules need data fetching and real-time updates | F3–F7,F9
15 | F7 | Admin Module | Kill switch UI needed for E2E kill switch tests | Q6
16 | Q5 | E2E Cycle | Final validation that everything works together | Release gate
17 | Q6 | Kill Switch E2E | Safety validation — must pass before any live trading | Release gate
18 | D1 | Docker | All other DevOps and local dev depends on containers | D2,D4,D5